## Cover
HANOI UNIVERSITY OF SCIENCE AND TECHNOLOGY
School of Information and communications technology
Test Plan
Version 1.0
AIMS Project
Subject: ITSS Software Development
<Group 25>
<List of participants>
Hanoi, May, 2026

## Table of Contents
Table of Contents
1 | Instructions
2 | Overall Description
3 | Testing Approach Strategy'
4 | 'Unit Testing Summary'!A1
5 | 'Test Case Details'!A1

## Introduction
1. Introduction
1.1. Objective
This Unit Test Plan defines the objectives, scope, approach, and detailed unit test coverage for the AIMS system. The document is intended for developers, testers, project members, instructors, and reviewers who need to understand how the main business logic is verified at unit level. The purpose of this document is to ensure that individual methods, services, validators, and calculation units are tested independently before being integrated into higher-level system testing. Based on the current test case details, the plan covers the unit testing phase for key AIMS functions, including Place Order, VietQR payment, PayPal payment, Product Management, and View Product Detail. This document may be updated when requirements, implementation details, business rules, or test cases change. All tests are designed to avoid real external transactions and protect sensitive information by using mocked repositories, simulated gateway responses, and sample tokens instead of real payment credentials or production data.
1.2 Scope
The software product covered by this test plan is the AIMS application, an e-commerce/media product management system that supports ordering, delivery information, invoice calculation, shipping fee calculation, online payment, product administration, and product detail viewing. The unit testing scope focuses on verifying the correctness of core backend logic and service-level behavior. The tested components include: - Order item subtotal calculation and invoice total calculation. - Order placement stock checking. - Delivery information validation for name, phone number, and address. - Shipping fee calculation based on province and package weight. - VietQR transaction creation, QR generation, token validation, and gateway callback handling. - PayPal order creation, capture processing, refund processing, and gateway routing. - Product field validation, product creation/update, price range checking, deletion/deactivation rules, and stock adjustment. - Product detail access rules for Customers and Product Managers. This plan does not cover full user interface testing, real payment gateway execution, live database transactions, browser rendering, or end-to-end integration flows. Those areas should be verified in integration, system, or acceptance testing phases.
1.3. Glossary
AIMS: The application under test, used for ordering and managing media products. Unit Test: A test that verifies an individual function, method, class, or service in isolation. Test Case: A specific testing scenario with input data, expected output, actual output, and pass/fail result. Use Case: A functional scenario that represents user/system interaction, such as Place Order or Pay by PayPal. EP (Equivalence Partitioning): A test design technique that groups input values into valid and invalid classes. BVA (Boundary Value Analysis): A test design technique that checks values at, below, and above important limits. Decision Table: A test design technique used when output depends on combinations of conditions. Mock: A simulated dependency used to isolate the unit under test from external systems, databases, or APIs. Gateway: An external payment service such as VietQR or PayPal. DTO (Data Transfer Object): A structured object used to transfer data between layers of the application. Exception: An error object thrown when business rules or validation rules are violated.
1.4. References
Project test artifacts contained in this workbook: - Testing Approach/Strategy - Unit Testing Summary - Test Case Details Template and testing references: - Centers for Medicare & Medicaid Services. Test Case Specification. - Centers for Medicare & Medicaid Services. Test Plan. - Guru99. Sample Test Case Template formats.

## Overall Description
2. Overall Description
2.1. General Overview
AIMS is an e-commerce/media store system that allows users to browse products, view product details, place orders, provide delivery information, and complete payments. Product Managers can maintain product information, update prices, manage stock, and control product visibility. The tested modules support the main transaction flow from selecting items to calculating payment amounts and handling payment results. The current unit test plan concentrates on five main use cases: - UC01: Place Order. - UC02: Pay by VietQR. - UC03: Pay by PayPal. - UC04: Product Management. - UC05: View Product Detail. The system logic is organized around service and domain methods such as OrderItem.calculateSubTotal(), Invoice.calculateTotalAmount(), OrderService.requestToPlaceOrder(), DeliveryInfo validators, ShippingService.calculateShippingFee(), PaymentService methods, VietQRService.generateQRCode(), and ProductService methods. These units are tested independently using sample inputs, mocked repositories, mocked payment gateway responses, and expected exceptions. The test cases were designed using Equivalence Partitioning, Boundary Value Analysis, and Decision Table Testing. The test coverage includes normal successful flows, invalid input handling, boundary values, business rule enforcement, token/security validation, payment callback status handling, refund scenarios, product deletion constraints, and role-based product detail visibility.
2.2. Assumptions/Constraints/Risks
2.2.1. Assumptions
The following assumptions are made for this unit testing plan: - The unit tests are executed in a controlled development or test environment, not in production. - External systems such as VietQR, PayPal, databases, and repositories are mocked or stubbed. - Sample payment tokens are used to represent valid, expired, missing, or invalid authentication states. - Business rules in the test cases reflect the current understanding of AIMS requirements. - Each unit under test can be executed independently without requiring a full user interface or live backend deployment. - Required testing frameworks and dependencies, such as Jest for the NestJS/TypeScript backend, are available in the test environment. - Test input data is synthetic and does not contain real customer payment information.
2.2.2. Constraints
The unit testing activity is subject to the following constraints: - Tests are limited to unit-level behavior and do not verify complete end-to-end user journeys. - Real payment execution through VietQR or PayPal is outside the unit testing scope. - Live database operations are not performed; repository behavior is simulated through mocks. - User interface layout, browser rendering, and visual behavior are not evaluated in this document. - Test accuracy depends on the correctness of mocked data and mocked service behavior. - Changes in business rules, external gateway APIs, or DTO structures may require updates to test cases. - Some scenarios, such as payment gateway timeout or transaction-not-found cases, are verified through simulated responses rather than real failures.
2.2.3. Risks
The main risks associated with this unit testing plan are: - Mocked dependencies may not fully represent real behavior of databases or payment gateways. Mitigation: add integration tests after unit testing. - Business rules may change after the test cases are written. Mitigation: review and update the traceability matrix and test case details whenever requirements change. - Payment and security flows may be more complex in production than in unit tests. Mitigation: supplement unit tests with security, integration, and end-to-end payment sandbox testing. - Boundary values may be incomplete if requirements are ambiguous. Mitigation: validate limits such as price range, shipping thresholds, deletion limits, and token rules with the project specification. - Duplicate or inconsistent test case IDs may reduce traceability. Mitigation: standardize naming conventions before final submission. - High pass rates may hide insufficient coverage if only expected scenarios are tested. Mitigation: include negative cases, exception cases, and decision-table combinations as shown in the Test Case Details sheet.

## Testing Approach Strategy
3. Testing Approach/Strategy
3.1. Overview A systematic approach ensures thorough testing of all relevant aspects of a unit. - Test-Driven Development (TDD): Students are encouraged to write test cases before implementing code to drive the design and development process. - Behavior-Driven Testing: Focus on validating expected behavior of the code based on requirements or specifications. - Automation First: Unit tests should be automated to allow repeated execution and integration into CI/CD pipelines. - Mocking and Isolation: Use mocks, stubs, or fakes to isolate the unit under test from dependencies like external APIs, databases, or other modules. Example: A unit test for a login function should validate all possible outcomes, such as successful login, invalid credentials, and locked accounts, without relying on the actual database. 3.2. Scope of Unit Testing In-Scope Components Core Business Logic: Domain-specific calculations, state mutations, operational workflows, and algorithmic data pipelines. Input Validation Subroutines: Strict format checking, parameter constraints, and alphanumeric string filtering (e.g., telephone numbers, email patterns, currency structures). Boundary Conditions & Edge Cases: Off-by-one errors, array indices bounds, zero-value conditions, and maximum structural capacities. Error and Exception Vectors: Verifying that custom or native application exceptions are explicitly thrown and handled when unexpected runtime values occur. Out-of-Scope Components External Integration Layers: Real network calls, physical handshake protocols, and live web services endpoints. User Interfaces (UI): Graphical layouts, browser page renders, frontend styling properties, and visual DOM structures. Live Database Operations: Physical row insertions, permanent state changes in storage engines, and live transactional commits (all database states must be simulated via memory repositories or stubs).
3.3. Strategy for Designing Unit Tests The test design focuses on the following systematic techniques: Equivalence Partitioning (EP): Input data is divided into valid and invalid partitions. Only one representative value from each partition is tested to reduce the total number of test cases while maintaining effectiveness. Example: For product prices, numbers between 30% and 150% of the original price are grouped as a valid partition, while negative numbers are grouped as an invalid partition. Boundary Value Analysis (BVA): Most software errors occur at the extreme edges of input ranges. Test cases are specifically designed to check values exactly on, immediately below, and immediately above the logical boundaries. Example: Testing product deletion constraints at exactly 0 items (lower bound), 10 items (maximum bulk bound), and 11 items (exceeding limit threshold). Decision Table Testing: This technique is used for complex business logic that involves multiple combinations of inputs and system states. Example: Mapping the different combination outcomes of payment gateway webhooks (e.g., handling COMPLETED, DECLINED, or CANCELED payment status callbacks from PayPal). 3.4. Tools and Frameworks Jest Framework - FOR Nestjs ( TypeScript )

## Unit Testing Summary
4.1. Traceability Matrix Mapped to Use Cases
Use Case ID |  |  | UC01: Place Order | UC02: Pay by VietQR | UC03: Pay by PayPal | UC04: PM (Product Management) | UC05: View Product Detail
Test Case ID | Test Case Title | Totals | 32 | 14 | 32 | 26 | 5
O_TC01 - O_TC06 | Item Subtotal Calculation | 6 | X
O_TC07 - O_TC12 | Invoice Total Payment Calculation | 6 | X
O_TC13 - O_TC14 | Stock Checking If Place Order | 2 | X
O_TC15 - O_TC28 | Delivery Information Validation | 14 | X
O_TC29 - O_TC32 | Shipping Fee Calculation | 4 | X
M_TC01 - M_TC03 | Payment Transaction Records | 3 |  | X
M_TC04 - M_TC05 | VietQR QR Code Generation | 2 |  | X
M_TC06 - M_TC08 | VietQR Access Token Authentication | 3 |  | X
M_TC09 - M_TC11 | VietQR Gateway Callback Result | 2 |  | X
M_TC12 - M_TC13 | VietQR QR Response Parsing | 2 |  | X
M_TC14 - M_TC14 | VietQR Generate Request Payload Construction | 1 |  | X
P_TC01 - P_TC04 | PayPal Order Creation | 4 |  |  | X
P_TC05 - P_TC10 | PayPal Capture Processing | 6 |  |  | X
P_TC19 - P_TC29 | PayPal Refund Processing | 11 |  |  | X
P_TC30 - P_TC32 | PayPal Through Gateway Service | 3 |  |  | X
P_TC01 - P_TC04 | Product Field Validation Success Cases | 4 |  |  |  | X
P_TC05 - P_TC08 | Product Field Update Validation Rules | 4 |  |  |  | X
P_TC09 - P_TC13 | New Product Catalog Creation | 5 |  |  |  | X
P_TC14 - P_TC17 | Product Pricing Range Check | 4 |  |  |  | X
P_TC18 - P_TC23 | Product Deactivation & Deletion | 6 |  |  |  | X
P_TC24 - P_TC26 | Stock Adjustment With Reasons | 3 |  |  |  | X
V_TC01 - V_TC05 | View Product Details | 5 |  |  |  |  | X
4.2. Test Suite for UC01-"Place Order"
Test Suite ID | Test Suite Title |  | Description |  |  | Test Cases
US001 | Place Order Unit Test Suite |  | Covers unit methods: OrderItem.calculateSubTotal(), Invoice.calculateTotalAmount(), OrderService.requestToPlaceOrder(), DeliveryInfo.validateName(), DeliveryInfo.validatePhone(), DeliveryInfo.validateAddress(), ShippingService.calculateShippingFee(). |  |  | O_TC01 - O_TC32
4.2. Test Suite for UC02-"Pay Order (VietQR)"
Test Suite ID | Test Suite Title |  | Description |  |  | Test Cases
US002 | Pay Order (VietQR) Unit Test Suite |  | Covers unit methods: VietQRPaymentService.createTransaction(), VietQRService.generateQRCode(), VietQRPaymentService.processPaymentResult(), QRCode.parseQRCodeResponse(), QRGenerateRequest.buildRequestString(). |  |  | M_TC01 - M_TC14
4.2. Test Suite for UC03-"Pay Order (PayPal)"
Test Suite ID | Test Suite Title |  | Description |  |  | Test Cases
US003 | Pay Order (PayPal) Unit Test Suite |  | Covers PayPal payment flow in PaymentService.payThroughGatewayService(): access token validation, order creation, capture processing, and refund processing. |  |  | P_TC01 - P_TC32
4.2. Test Suite for UC04-"Product Management"
Test Suite ID | Test Suite Title |  | Description |  |  | Test Cases
US004 | Product Management Unit Test Suite |  | Covers unit methods: ProductService.validateBookFields(), ProductService.validateNewspaperFields(), ProductService.validateCDFields(), ProductService.validateDVDFields(), ProductService.createProduct(), ProductService.handleUpdate(), ProductService.handleDeletion(), Product.changeQuantityInStock(). |  |  | P_TC01 - P_TC26
4.2. Test Suite for UC05-"View Product Detail"
Test Suite ID | Test Suite Title |  | Description |  |  | Test Cases
US005 | View Product Detail Unit Test Suite |  | Covers unit method: ProductService.viewProductDetails(). |  |  | V_TC01 - V_TC05

## Test Case Details
5. DETAILED SPECIFICATION OF VERIFIED UNIT TEST CASES
Test Case ID | Test Case Name | Detailed Description | Unit Under Test (Method) | Input Data | Expected Output | Actual Output | Pass/Fails | Notes
O_TC01 | CalculateSubtotalNormal | Verify correct subtotal calculation with positive integers [EP]. | OrderItem.calculateSubTotal() | quantity: 4, unitPrice: 30000 | 120000 | Passed | Pass | -
O_TC02 | CalculateSubtotalMinBound | Verify subtotal calculation at the minimum valid boundary [BVA]. | OrderItem.calculateSubTotal() | quantity: 1, unitPrice: 1 | 1 | Passed | Pass | -
O_TC03 | CalculateSubtotalZeroQty | Verify exception when order quantity is exactly 0 [BVA]. | OrderItem.calculateSubTotal() | quantity: 0, unitPrice: 30000 | InvalidQuantityException | Passed | Pass | -
O_TC04 | CalculateSubtotalNegativeQty | Verify exception when order quantity is negative [EP]. | OrderItem.calculateSubTotal() | quantity: -5, unitPrice: 30000 | InvalidQuantityException | Passed | Pass | -
O_TC05 | CalculateSubtotalZeroUnitPrice | Verify exception when unit price is exactly 0 [BVA]. | OrderItem.calculateSubTotal() | quantity: 2, unitPrice: 0 | InvalidPriceException | Passed | Pass | -
O_TC06 | CalculateSubtotalNegativeUnitPrice | Verify exception when unit price is negative [EP]. | OrderItem.calculateSubTotal() | quantity: 2, unitPrice: -15000 | InvalidPriceException | Passed | Pass | -
O_TC07 | AggregateGrandTotalNormal | Verify grand total matches sum of item subtotals plus shipping fee with no discount applied [EP]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: 80000, shippingFee: 22000 | 102000 | Passed | Pass | -
O_TC08 | AggregateTotalNegativeShippingError | Verify exception when shipping fee input parameter is negative [EP]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: 500000, shippingFee: -10000 | InvalidPriceException | Passed | Pass | -
O_TC09 | AggregateTotalNegativeSubtotalError | Verify exception when items subtotal sum is negative [EP]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: -50000, shippingFee: 45000 | InvalidPriceException | Passed | Pass | -
O_TC10 | AggregateTotalWithFullFreeShipDiscount | Verify total when items total > 100k and shipping fee is fully covered (< 25k) [Decision Table]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: 150000, shippingFee: 22000 | 150000 | Passed | Pass | -
O_TC11 | AggregateTotalWithMaxFreeShipDiscount | Verify total when items total > 100k and shipping fee exceeds max discount (25k) [Decision Table]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: 150000, shippingFee: 30000 | 155000 | Passed | Pass | -
O_TC12 | AggregateTotalAtFreeShipThresholdBound | Verify total when items total is exactly 100k boundary (No discount applied) [BVA]. | Invoice.calculateTotalAmount(subtotal: number, shippingFee: number) | subtotal: 100000, shippingFee: 22000 | 122000 | Passed | Pass | -
O_TC13 | RequestPlaceOrderStockAvailable | Verify successful order creation when all items are in stock [Decision Table]. | OrderService.requestToPlaceOrder() | Mock: ProductRepository confirms enough stock for all items. | PENDING | Passed | Pass | -
O_TC14 | RequestPlaceOrderStockShortage | Verify order creation fails when any item is out of stock [Decision Table]. | OrderService.requestToPlaceOrder() | Mock: At least one item exceeds available stock in warehouse. | InsufficientStockException | Passed | Pass | -
O_TC15 | ValidateNameSuccess | Verify valid name containing only letters within 30 characters [EP]. | DeliveryInfo.validateName(name: string) | name: 'Son Nguyen' | TRUE | Passed | Pass | -
O_TC16 | ValidateNameNullError | Verify error when name string is empty or null [BVA]. | DeliveryInfo.validateName(name: string) | name: '' | ValidationException | Passed | Pass | -
O_TC17 | ValidateNameTooLongError | Verify error when name length exceeds 30 characters boundary [BVA]. | DeliveryInfo.validateName(name: string) | name: 'Son Nguyen Son Nguyen Son Nguyen S' (31 chars) | ValidationException | Passed | Pass | -
O_TC18 | ValidateNameInvalidCharError | Verify error when name contains numbers or special characters [EP]. | DeliveryInfo.validateName(name: string) | name: 'Son123!' | ValidationException | Passed | Pass | -
O_TC19 | ValidatePhoneSuccess | Verify valid 10-digit phone number starting with digit 0 [BVA]. | DeliveryInfo.validatePhone(phone: string) | phone: '0987654321' | TRUE | Passed | Pass | -
O_TC20 | ValidatePhoneWithSeparatorSuccess | Verify valid phone number containing single type separator dots [EP]. | DeliveryInfo.validatePhone(phone: string) | phone: '098.765.43.21' | TRUE | Passed | Pass | -
O_TC21 | ValidatePhoneMixedSeparatorsError | Verify error when phone contains mixed types of separators [Decision Table]. | DeliveryInfo.validatePhone(phone: string) | phone: '098.765-43/21' | ValidationException | Passed | Pass | -
O_TC22 | ValidatePhoneNotStartWithZeroError | Verify error when phone number does not start with digit 0 [EP]. | DeliveryInfo.validatePhone(phone: string) | phone: '1987654321' | ValidationException | Passed | Pass | -
O_TC23 | ValidatePhoneInvalidLengthError | Verify error when total digits count is below 10 [BVA]. | DeliveryInfo.validatePhone(phone: string) | phone: '098765432' | ValidationException | Passed | Pass | -
O_TC24 | ValidatePhoneInvalidCharError | Verify error when phone string contains alphabetic characters [EP]. | DeliveryInfo.validatePhone(phone: string) | phone: '0987654ABC' | ValidationException | Passed | Pass | -
O_TC25 | ValidateAddressSuccess | Verify valid address containing letters, digits, and slashes within 100 characters [EP]. | DeliveryInfo.validateAddress(address: string) | address: '123/45 Hanoi' | TRUE | Passed | Pass | -
O_TC26 | ValidateAddressNullError | Verify error when address string is empty or null [BVA]. | DeliveryInfo.validateAddress(address: string) | address: '' | ValidationException | Passed | Pass | -
O_TC27 | ValidateAddressTooLongError | Verify error when address length exceeds 100 characters boundary [BVA]. | DeliveryInfo.validateAddress(address: string) | String of 101 valid characters. | ValidationException | Passed | Pass | -
O_TC28 | ValidateAddressInvalidCharError | Verify error when address contains disallowed special characters [EP]. | DeliveryInfo.validateAddress(address: string) | address: 'Hanoi@2026!' | ValidationException | Passed | Pass | -
O_TC29 | CalculateShippingFeeHnHcmBaseEdge | Verify base shipping fee for HN/HCM at exactly 3kg boundary [BVA]. | ShippingService.calculateShippingFee(province: string, weight: number) | province: 'Ha Noi', weight: 3.0 | 22000 | Passed | Pass | -
O_TC30 | CalculateShippingFeeHnHcmProgressive | Verify progressive fee for HN/HCM when weight exceeds 3kg by one block [BVA]. | ShippingService.calculateShippingFee(province: string, weight: number) | province: 'Ha Noi', weight: 3.5 | 24500 | Passed | Pass | -
O_TC31 | CalculateShippingFeeOtherBaseEdge | Verify base shipping fee for other provinces at exactly 0.5kg boundary [BVA]. | ShippingService.calculateShippingFee(province: string, weight: number) | province: 'Da Nang', weight: 0.5 | 30000 | Passed | Pass | -
O_TC32 | CalculateShippingFeeOtherProgressive | Verify progressive fee for other provinces when weight exceeds 0.5kg by one block [BVA]. | ShippingService.calculateShippingFee(province: string, weight: number) | province: 'Da Nang', weight: 1.0 | 32500 | Passed | Pass
P_TC01 | ValidateBookFieldsSuccess | Verify Book validator passes when all required fields (author, coverType, publisher, publicationDate) are valid [EP]. | ProductService.validateBookFields(data: BookDTO) | type: 'Book', author: 'Author A', coverType: 'paperback', publisher: 'Publisher X', publicationDate: '2026-01-01' | TRUE | Passed | Pass | Used in both Create and Update
P_TC02 | ValidateNewspaperFieldsSuccess | Verify Newspaper validator passes when all required fields (editorInChief, publisher, publicationDate) are valid [EP]. | ProductService.validateNewspaperFields(data: NewspaperDTO) | type: 'Newspaper', editorInChief: 'Editor B', publisher: 'Publisher Y', publicationDate: '2026-05-19' | TRUE | Passed | Pass | Used in both Create and Update
P_TC03 | ValidateCDFieldsSuccess | Verify CD validator passes when all required fields (artists, recordLabel, tracksList, genre) are valid [EP]. | ProductService.validateCDFields(data: CDDTO) | type: 'CD', artists: 'Artist C', recordLabel: 'Label Z', tracksList: [{title: 'Track 1', length: '3:45'}], genre: 'Pop' | TRUE | Passed | Pass | Used in both Create and Update
P_TC04 | ValidateDVDFieldsSuccess | Verify DVD validator passes when all required fields (discType, director, runtime, studio, language, subtitles) are valid [EP]. | ProductService.validateDVDFields(data: DVDDTO) | type: 'DVD', discType: 'Blu-ray', director: 'Director D', runtime: 120, studio: 'Studio M', language: 'English', subtitles: 'Vietnamese' | TRUE | Passed | Pass | Used in both Create and Update
P_TC05 | ValidateBookFieldsMissingError | Verify Book validator throws error when a mandatory field is missing or accidentally cleared during update [Decision Table]. | ProductService.validateBookFields(data: BookDTO) | action: 'UPDATE', type: 'Book', updatedData: { author: '', coverType: 'paperback' } | ValidationException | Passed | Pass | -
P_TC06 | ValidateNewspaperFieldsMissingError | Verify Newspaper validator throws error when a mandatory field is missing or accidentally cleared during update [Decision Table]. | ProductService.validateNewspaperFields(data: NewspaperDTO) | action: 'UPDATE', type: 'Newspaper', updatedData: { editorInChief: '', publisher: 'Publisher Y' } | ValidationException | Passed | Pass | -
P_TC07 | ValidateCDFieldsMissingError | Verify CD validator throws error when tracksList is empty or cleared during update [Decision Table]. | ProductService.validateCDFields(data: CDDTO) | action: 'UPDATE', type: 'CD', updatedData: { artists: 'Artist C', tracksList: [] } | ValidationException | Passed | Pass | -
P_TC08 | ValidateDVDFieldsMissingError | Verify DVD validator throws error when a mandatory field is missing or accidentally cleared during update [Decision Table]. | ProductService.validateDVDFields(data: DVDDTO) | action: 'UPDATE', type: 'DVD', updatedData: { discType: '', director: 'Director D' } | ValidationException | Passed | Pass | -
P_TC09 | CreateBookSuccess | Verify successful Book creation when barcode is unique and its specific validator passes [EP]. | ProductService.createProduct(payload: CreateProductDTO) | type: 'Book', barcode: '89301' / Mock: validateBookFields returns true. | Object with auto-increment ID | Passed | Pass | -
P_TC10 | CreateNewspaperSuccess | Verify successful Newspaper creation when barcode is unique and its specific validator passes [EP]. | ProductService.createProduct(payload: CreateProductDTO) | type: 'Newspaper', barcode: '89302' / Mock: validateNewspaperFields returns true. | Object with auto-increment ID | Passed | Pass | -
P_TC11 | CreateCDSuccess | Verify successful CD creation when barcode is unique and its specific validator passes [EP]. | ProductService.createProduct(payload: CreateProductDTO) | type: 'CD', barcode: '89303' / Mock: validateCDFields returns true. | Object with auto-increment ID | Passed | Pass | -
P_TC12 | CreateDVDSuccess | Verify successful DVD creation when barcode is unique and its specific validator passes [EP]. | ProductService.createProduct(payload: CreateProductDTO) | type: 'DVD', barcode: '89304' / Mock: validateDVDFields returns true. | Object with auto-increment ID | Passed | Pass | -
P_TC13 | CreateProductDuplicateBarcode | Verify duplicate barcode throws a conflict exception [EP]. | ProductService.createProduct(payload: CreateProductDTO) | barcode: '89301', name: 'Duplicate Product' / Mock: Barcode '89301' already exists in DB. | ConflictException | Passed | Pass | -
P_TC14 | UpdatePriceMinValidBound | Verify successful update at the minimum price boundary (30%) [BVA]. | ProductService.handleUpdate(productID: number, payload: UpdateProductDTO) | originalPrice: 100000, newPrice: 30000 | Database updated successfully | Passed | Pass | -
P_TC15 | UpdatePriceMinInvalidBound | Verify block when price falls below minimum boundary (29.99%) [BVA]. | ProductService.handleUpdate(productID: number, payload: UpdateProductDTO) | originalPrice: 100000, newPrice: 29999 | InvalidPriceException | Passed | Pass | -
P_TC16 | UpdatePriceMaxValidBound | Verify successful update at the maximum price boundary (150%) [BVA]. | ProductService.handleUpdate(productID: number, payload: UpdateProductDTO) | originalPrice: 100000, newPrice: 150000 | Database updated successfully | Passed | Pass | -
P_TC17 | UpdatePriceMaxInvalidBound | Verify block when price exceeds maximum boundary (150.01%) [BVA]. | ProductService.handleUpdate(productID: number, payload: UpdateProductDTO) | originalPrice: 100000, newPrice: 150001 | InvalidPriceException | Passed | Pass | -
P_TC18 | SoftDeleteWithStock | Verify single soft-delete triggers when product stock is greater than 0 [Decision Table]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [10] / Mock: Product 10 has quantityInStock > 0. | status = deactivated | Passed | Pass | -
P_TC19 | HardDeleteNoStock | Verify single hard-delete triggers when product stock equals 0 [Decision Table]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [11] / Mock: Product 11 has quantityInStock = 0. | Removed from database | Passed | Pass | -
P_TC20 | BulkDeleteAtMaxBound | Verify bulk deletion succeeds for exactly 10 products with zero stock in one request [BVA]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [1,2,3,4,5,6,7,8,9,10] / Mock: All 10 products have stock = 0. | 10 items removed from database | Passed | Pass | Ngưỡng xóa đồng thời max
P_TC21 | BulkDeleteExceedMaxBoundError | Verify block when attempting to delete more than 10 products simultaneously [BVA]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [1,2,3,4,5,6,7,8,9,10,11] (11 items) | InvalidOperationException | Passed | Pass | Vượt ngưỡng xóa đồng thời
P_TC22 | DailyDeleteAtMaxLimit | Verify deletion succeeds when within the daily security limit of 20 products [BVA]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [12,13] / Mock: Manager already deleted 18 products today (Total = 20). | Removed from database | Passed | Pass | Ngưỡng bảo mật trong ngày
P_TC23 | DailyDeleteExceedLimitError | Verify block when total deletions exceed the daily security limit of 20 products [BVA]. | ProductService.handleDeletion(productIDs: number[]) | productIDs: [14] / Mock: Manager already deleted 20 products today (Total = 21). | SecurityLimitException | Passed | Pass | Vượt giới hạn bảo mật ngày
P_TC24 | ManualAdjustmentWithReasonSuccess | Verify manual stock adjustment succeeds when an explicit reason is provided [Decision Table]. | Product.changeQuantityInStock(newStock: number, isManualAdjustment: boolean, reason: string) | isManualAdjustment: true, newStock: 15, reason: 'Restocking damaged items' | Database updated with reason logged | Passed | Pass | Điều chỉnh thủ công hợp lệ
P_TC25 | ManualAdjustmentMissingReasonError | Verify validation exception when manual stock adjustment is performed without a reason [Decision Table]. | Product.changeQuantityInStock(newStock: number, isManualAdjustment: boolean, reason: string) | isManualAdjustment: true, newStock: 15, reason: '' | ValidationException | Passed | Pass | Chặn điều chỉnh thiếu lý do
P_TC26 | DeductStockBelowZeroError | Verify manual reduction fails when it causes negative stock counter [BVA]. | Product.changeQuantityInStock(newStock: number, isManualAdjustment: boolean, reason: string) | isManualAdjustment: true, currentStock: 5, deductAmount: 6, reason: 'Remove damaged' | OutOfStockException | Passed | Pass | -
M_TC01 | CreateTransactionSuccess | Verify transaction record creation with positive valid amount [EP]. | VietQRPaymentService.createTransaction(invoiceId: number, amount: number, method: string) | invoiceId: 1, amount: 200000, method: 'VietQR' | Transaction object created with invoiceId: 1, amount: 200000, method: 'VietQR', status: 'PENDING' and saved to repository. | Passed | Pass | -
M_TC02 | CreateTransactionMinBound | Verify transaction creation at the minimum valid amount boundary [BVA]. | VietQRPaymentService.createTransaction(invoiceId: number, amount: number, method: string) | invoiceId: 1, amount: 1, method: 'VietQR' | Transaction object created with amount: 1 and status: 'PENDING'. | Passed | Pass | Minimum valid amount boundary
M_TC03 | CreateTransactionInvalidAmountError | Verify block when transaction amount is exactly zero [BVA]. | VietQRPaymentService.createTransaction(invoiceId: number, amount: number, method: string) | invoiceId: 1, amount: 0, method: 'VietQR' | InvalidAmountException | Passed | Pass | Block zero or negative transaction amount
M_TC04 | GenerateQRSuccess | Verify QR URL generation when payment gateway responds normally and a valid token is provided [EP]. | VietQRService.generateQRCode(amount: number, token: string) | amount: 200000, token: 'VALID_JWT_TOKEN' / Mock: VietQR API returns { qrLink: '[URL]' }. | Exact QR image URL string: [URL] | Passed | Pass | -
M_TC05 | GenerateQRGatewayError | Verify error handling when the payment gateway fails or times out [EP]. | VietQRService.generateQRCode(amount: number, token: string) | amount: 200000, token: 'VALID_JWT_TOKEN' / Mock: VietQR API throws Error('timeout'). | PaymentGatewayException | Passed | Pass | Failure from gateway side
M_TC06 | GenerateQRExpiredTokenError | Verify QR generation is blocked when access token is expired [BVA]. | VietQRService.generateQRCode(amount: number, token: string) | amount: 200000, token: 'EXPIRED_JWT_TOKEN' | TokenExpiredException | Passed | Pass | Block expired security token
M_TC07 | GenerateQRInvalidTokenError | Verify QR generation is blocked when access token signature is invalid or tampered [EP]. | VietQRService.generateQRCode(amount: number, token: string) | amount: 200000, token: 'INVALID_SIGNATURE_TOKEN' | InvalidTokenException | Passed | Pass | Block invalid token signature
M_TC08 | GenerateQRMissingTokenError | Verify QR generation is blocked when access token is missing or empty [BVA]. | VietQRService.generateQRCode(amount: number, token: string) | amount: 200000, token: '' | MissingTokenException | Passed | Pass | Block completely missing token
M_TC09 | ProcessPaymentCallbackSuccess | Verify transaction status updates upon successful gateway callback [Decision Table]. | PaymentService.processPaymentResult(callbackStatus: string, currentStatus: string) | callbackStatus: 'SUCCESS', currentStatus: 'PENDING' / Mock: repository returns latest pending transaction. | Transaction status updated to SUCCESS and transaction is saved to repository. | Passed | Pass | Successful payment callback flow
M_TC10 | ProcessPaymentCallbackFailed | Verify transaction status updates upon failed gateway callback [Decision Table]. | PaymentService.processPaymentResult(callbackStatus: string, currentStatus: string) | callbackStatus: 'FAILED', currentStatus: 'PENDING' / Mock: repository returns latest pending transaction. | Transaction status updated to FAILED and transaction is saved to repository. | Passed | Pass | Failed payment callback flow
M_TC11 | ProcessPaymentCallbackTransactionNotFound | Verify exception when no pending transaction is found for callback processing [EP]. | PaymentService.processPaymentResult(callbackStatus: string, currentStatus: string) | callbackStatus: 'SUCCESS', currentStatus: 'PENDING' / Mock: repository returns null. | TransactionNotFoundException and repository save() is not called. | Passed | Pass | Block callback update when transaction does not exist
M_TC12 | ParseQRCodeResponseSuccess | Verify QR code domain object is parsed correctly from a valid gateway response [EP]. | QRCode.parseQRCodeResponse(response: any) | response: { qrLink: '[URL]', qrCode: '000201', amount: 200000 } | QRCode object contains qrLink, qrCode, and amount matching the response. | Passed | Pass | Valid QR response mapping
M_TC13 | ParseQRCodeMalformedResponseError | Verify malformed QR response is rejected when QR link is missing [EP]. | QRCode.parseQRCodeResponse(response: any) | response: { data: {} } | Error message: QR code response is missing QR link | Passed | Pass | Block invalid/malformed gateway response
M_TC14 | QRGenerateRequestSuccess | Verify QR generate request object can build a valid request string for VietQR API [EP]. | QRGenerateRequest.buildRequestString() | content: 'payment:200000', amount: 200000, orderId: 'ORDER-200000', bankCode: '970436', bankAccount: '1234567890', bankName: 'Vietcombank' | JSON request string contains correct content, amount, orderId, bankCode, bankAccount, and bankName. | Passed | Pass | Valid request payload construction
V_TC01 | ViewActiveProductAsCustomerSuccess | Verify Customer can successfully view details of an active product [Decision Table]. | ProductService.viewProductDetails(productID: number, userRole: string) | productID: 101, userRole: 'Customer' / Mock: Product 101 has status: 'active'. | ProductDTO | Passed | Pass | -
V_TC02 | ViewDeactivatedProductAsCustomerError | Verify Customer is blocked from viewing a deactivated product [Decision Table]. | ProductService.viewProductDetails(productID: number, userRole: string) | productID: 102, userRole: 'Customer' / Mock: Product 102 has status: 'deactivated'. | ProductHiddenException | Passed | Pass | Block customer from viewing hidden products
V_TC03 | ViewActiveProductAsPMSuccess | Verify Product Manager can successfully view details of an active product [Decision Table]. | ProductService.viewProductDetails(productID: number, userRole: string) | productID: 101, userRole: 'ProductManager' / Mock: Product 101 has status: 'active'. | ProductDTO | Passed | Pass | -
V_TC04 | ViewDeactivatedProductAsPMSuccess | Verify Product Manager can successfully view details of a deactivated/hidden product [Decision Table]. | ProductService.viewProductDetails(productID: number, userRole: string) | productID: 102, userRole: 'ProductManager' / Mock: Product 102 has status: 'deactivated'. | ProductDTO | Passed | Pass | PM can view hidden products for editing
V_TC05 | ViewProductNotFoundError | Verify exception is thrown when the product ID does not exist or is invalid in the database [BVA]. | ProductService.viewProductDetails(productID: number, userRole: string) | productID: 99999, userRole: 'Customer' / Mock: ProductRepository returns null. | ProductNotFoundException | Passed | Pass | Includes invalid ID cases
P_TC_01 | MissingAccessToken | Verify that the method throws a MissingTokenException if the access token parameter is empty or null [BVA]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: 100 }, token: '' | MissingTokenException | Passed | Pass | -
P_TC_02 | ExpiredAccessToken | Verify that the method throws a TokenExpiredException if an expired validation token string is supplied [EP]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: 100 }, token: 'EXPIRED_JWT_TOKEN' | TokenExpiredException | Passed | Pass | -
P_TC_03 | CorruptedAccessToken | Verify that the method throws an InvalidTokenException if the token contains a corrupted or invalid cryptographic signature [EP]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: 100 }, token: 'INVALID_SIGNATURE_TOKEN' | InvalidTokenException | Passed | Pass | -
P_TC_04 | CreateMissingAllParams | Verify that an InvalidInvoiceException is raised when the input payload parameters object is completely empty [BVA]. | PaymentService.createOrder() | payload: {}, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_05 | CreateMissingTotalPayment | Verify that an InvalidInvoiceException is raised when the mandatory totalPayment property is omitted [EP]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123' }, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_06 | CreateMissingInvoiceID | Verify that an InvalidInvoiceException is raised when the mandatory invoiceID tracker property is omitted [EP]. | PaymentService.createOrder() | payload: { totalPayment: 100 }, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_07 | CreateZeroAmountBound | Verify that an InvalidPriceException is raised when the payment execution total is set to exactly 0 [BVA]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: 0 }, token: 'VALID_JWT_TOKEN' | InvalidPriceException | Passed | Pass | -
P_TC_08 | CreateNegativeAmountError | Verify that an InvalidPriceException is raised when the payment execution total falls into a negative range [EP]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: -50 }, token: 'VALID_JWT_TOKEN' | InvalidPriceException | Passed | Pass | -
P_TC_09 | CreateOrderSuccess | Verify that with valid security tokens and complete parameters, execution continues cleanly and returns the target gateway approval web link [EP]. | PaymentService.createOrder() | payload: { invoiceID: 'INV-123', totalPayment: 150 }, token: 'VALID_JWT_TOKEN' | https://paypal.com/approve/123' | Passed | Pass | -
P_TC_10 | MissingAccessToken | Verify that the method throws a MissingTokenException if the access token parameter is empty or null [BVA]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'COMPLETED' }, token: '' | MissingTokenException | Passed | Pass | -
P_TC_11 | ExpiredAccessToken | Verify that the method throws a TokenExpiredException if an expired validation token string is supplied [EP]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'COMPLETED' }, token: 'EXPIRED_JWT_TOKEN' | TokenExpiredException | Passed | Pass | -
P_TC_12 | CorruptedAccessToken | Verify that the method throws an InvalidTokenException if the token contains a corrupted or invalid cryptographic signature [EP]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'COMPLETED' }, token: 'INVALID_SIGNATURE_TOKEN' | InvalidTokenException | Passed | Pass | -
P_TC_13 | CaptureMissingAllParams | Verify that an InvalidInvoiceException is raised when the input callback payload object is completely empty [BVA]. | PaymentService.captureOrder() | payload: {}, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_14 | CaptureMissingStatus | Verify that an InvalidInvoiceException is raised when the mandatory captureStatus flag is omitted [EP]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789' }, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_15 | CaptureMissingOrderID | Verify that an InvalidInvoiceException is raised when the mandatory payPalOrderID key is omitted [EP]. | PaymentService.captureOrder() | payload: { captureStatus: 'COMPLETED' }, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_16 | CaptureTransactionNotFound | Verify that a TransactionNotFoundException is raised if the provided tracking key fails to resolve to an active transaction in the database [EP]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'NOT_FOUND', captureStatus: 'COMPLETED' }, token: 'VALID_JWT_TOKEN' | TransactionNotFoundException | Passed | Pass | -
P_TC_17 | StatusCompletedHappyPath | Verify that an incoming COMPLETED status mutates the transaction to APPROVED, updates database state, and flags order status as PAID [Decision Table]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'COMPLETED' }, token: 'VALID_JWT_TOKEN' | { success: true } | Passed | Pass | -
P_TC_18 | StatusDeclinedHandler | Verify that an incoming DECLINED status mutates the transaction to DENIED and throws an application PaymentGatewayException [Decision Table]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'DECLINED' }, token: 'VALID_JWT_TOKEN' | PaymentGatewayException | Passed | Pass | -
P_TC_19 | StatusCanceledHandler | Verify that an incoming CANCELED status mutates the transaction to CANCELED and throws an application PaymentGatewayException [Decision Table]. | PaymentService.captureOrder() | payload: { payPalOrderID: 'PP-789', captureStatus: 'CANCELED' }, token: 'VALID_JWT_TOKEN' | PaymentGatewayException | Passed | Pass | -
P_TC_20 | MissingAccessToken | Verify that the method throws a MissingTokenException if the access token parameter is empty or null [BVA]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 50 }, token: '' | MissingTokenException | Passed | Pass | -
P_TC_21 | ExpiredAccessToken | Verify that the method throws a TokenExpiredException if an expired validation token string is supplied [EP]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 50 }, token: 'EXPIRED_JWT_TOKEN' | TokenExpiredException | Passed | Pass | -
P_TC_22 | CorruptedAccessToken | Verify that the method throws an InvalidTokenException if the token contains a corrupted or invalid cryptographic signature [EP]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 50 }, token: 'INVALID_SIGNATURE_TOKEN' | InvalidTokenException | Passed | Pass | -
P_TC_23 | RefundMissingCaptureID | Verify that an InvalidInvoiceException is raised when the mandatory captureID parameter is completely omitted [EP]. | PaymentService.refundOrder() | payload: {}, token: 'VALID_JWT_TOKEN' | InvalidInvoiceException | Passed | Pass | -
P_TC_24 | RefundZeroAmountError | Verify that a PayPalRefundException is raised if the target amount property is explicitly set to exactly 0 [BVA]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 0 }, token: 'VALID_JWT_TOKEN' | PayPalRefundException | Passed | Pass | -
P_TC_25 | RefundNegativeAmountError | Verify that a PayPalRefundException is raised if the target amount property falls into a negative range [EP]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: -20 }, token: 'VALID_JWT_TOKEN' | PayPalRefundException | Passed | Pass | -
P_TC_26 | RefundTransactionNotFound | Verify that a PayPalRefundException is raised if the supplied captureID reference cannot be found in database records [EP]. | PaymentService.refundOrder() | payload: { captureID: 'NOT_FOUND', amount: 50 }, token: 'VALID_JWT_TOKEN' | PayPalRefundException | Passed | Pass | -
P_TC_27 | RefundExceedAmountError | Verify that execution is blocked and a PayPalRefundException is thrown if the requested refund amount exceeds the total value limit of the original transaction [BVA]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 150 }, token: 'VALID_JWT_TOKEN' | PayPalRefundException | Passed | Pass | -
P_TC_28 | RefundPartialSuccess | Verify successful partial balance execution when a valid partial value is defined, updating transaction state to REFUNDED [Decision Table]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123', amount: 40 }, token: 'VALID_JWT_TOKEN' | { success: true, refundID: 'REF-111' } | Passed | Pass | -
P_TC_29 | RefundFullSuccess | Verify that the method safely defaults to an automatic 100% full refund using the original balance when the amount field is completely omitted [Decision Table]. | PaymentService.refundOrder() | payload: { captureID: 'CAP-123' }, token: 'VALID_JWT_TOKEN' | { success: true, refundID: 'REF-222' } | Passed | Pass | -
P_TC_30 | RedirectToCreateOrder | Verify that when actionType equals PAYPAL_CREATE, internal payloads route directly to createOrder() and successfully resolve approval link variables [EP]. | PaymentService.payThroughGatewayService() | actionType: 'PAYPAL_CREATE', payload: { invoiceID: 'INV-123', totalPayment: 150 }, token: 'VALID_JWT_TOKEN' | https://paypal.com/approve/123' | Passed | Pass | -
P_TC_31 | RedirectToCaptureOrder | Verify that when actionType equals PAYPAL_CAPTURE, internal payloads route directly to captureOrder() and cleanly execute status updates [EP]. | PaymentService.payThroughGatewayService() | actionType: 'PAYPAL_CAPTURE', payload: { payPalOrderID: 'PP-789', captureStatus: 'COMPLETED' }, token: 'VALID_JWT_TOKEN' | { success: true } | Passed | Pass | -
P_TC_32 | RedirectToRefundOrder | Verify that when actionType equals PAYPAL_REFUND, internal payloads route directly to refundOrder() and smoothly process financial rollbacks [EP]. | PaymentService.payThroughGatewayService() | actionType: 'PAYPAL_REFUND', payload: { captureID: 'CAP-123' }, token: 'VALID_JWT_TOKEN' | { success: true, refundID: 'REF-222' } | Passed | Pass | -